## Sheet1
ACTIVITY | TASK | UNITS | UNIT COST ($) | TOTAL COST ($) | Activity TOTAL COST ($)
PLAN | identify stakholders and create engagment plan | 3 | 10 | 30 | 610
| create project charter | 4 | 20 | 80
| Build team and create team charter | 20 | 20 | 400
| Make schedule | 5 | 20 | 100
Design | create software architecture | 15 | 30 | 450 | 2100
| Review and rework software architecture | 5 | 10 | 50
| Draw flow charts | 40 | 20 | 800
| Draw sequence diagrams | 40 | 20 | 800 |  | PROJECT TOTAL COST ($)
implementation | Develop the front end | 50 | 50 | 2500 | 8000 | 13830
| develop the back end scripts | 60 | 50 | 3000
| build the database | 30 | 50 | 1500
| develop APIs | 20 | 50 | 1000
Testing | Test planing | 20 | 10 | 200 | 1950
| Test case development | 10 | 20 | 200
| Test Execution | 30 | 50 | 1500
| Test Cycle closure | 5 | 10 | 50
Closure | Maintenance | 10 | 50 | 500 | 1170
| Document Issues | 6 | 20 | 120
| Delivery | 10 | 50 | 500
| Celebration | 5 | 10 | 50